## Sheet1
Sno | Platform | Requirement | Requirement Details | Status | Developer | Target Date | Remarks
1 | D365 | Checkin code in PUAT/UAT | D365 Changes are done | Done | Vishnu | 2023-01-12
2 | D365 + dataverse | Testing of dual write | Testing of dual write | Done | Vishnu and Rohith | 2023-01-24
3 | Power pages | Balance view | Testing of view after Dual write | Done | Rohith | 2023-01-19
4 | JS | Ledger Allocation Rule | Form to enter Ledger allocation rule | WIP | James and Goutham | 2023-02-02 | james working on from account and to account filter in form using JS
5 | Power page | View of Allocation Balance As Per rule | Form to show Balance as per Allocaation rule | WIP | Goutham and James | 2023-01-31 | export to excel is done and filtering
6 | Logic | Logic to generate Allocation balance | Logic to generate Allocation balance | To be started | Rohith and Vishnu | 2023-02-05
7 | Over all | Over all testing |  | To be started | Rohit, Rohith and Vishnu | 2023-02-07
8 |  | Rework or bug correction |  | To be started |  | 2023-02-10

## Sheet2
Import Balance
| 4545001 |  | 20000 |  | C1 |  | D365 | this is in Page 17
| 46460001 |  | 5000 |  | C2
| 54545400 |  | 1000 |  | C1
| Ledger allocation rule |  | Data Entry
[8 empty] | Ledger1 | Ledger2
Header1 | 4545000..4546000 |  | C1 | Rule 1 |  |  |  | 4545000 | 4546000 | Page 19 Serial no 1 and 2 to be done in Javascript
Header 2 | 4646000..4747000 |  | C2 | Rule 2
Line | Rule 1 Details |  |  |  | Manual entry by user | java Script
Header 1 Line 1 | 4545601 | C2 | 20% |  | Total 100%
Header 1 Line 2 | 4545602 | C3 | 30%
Header 1 Line 3 | 4545603 | C4 | 50%
Rule 2 Details
Header 2 Line 1 | 4545701 | C5 | 25%
Header 2 Line 2 | 4545702 | C6 | 25%
Header 2 Line 3 | 4545703 | C7 | 50% | [6 empty] | Screen 1 | Screen 2 | Screen 3
[10 empty] | Balance from d365 | Rules | Output
View
| 4545601 | C2 | 20% | 200 |  | 4000 |  | Page 27 Inquiry form
| 4545602 | C3 | 30% | 300
| 4545603 | C4 | 40% | 500
| 4545701 | C5 | 0.25 | 1250
| 4545702 | C6 | 0.25 | 1250
| 4545703 | C7 | 0.5 | 2500
| 54545400 |  | 1000 |  | C1

## Sheet4
Header | Rule 1
Lines | Rule 1 | Line 1 | Ac1 | Ccc 1 | 25%
| Rule 1 | Line 2 | AC2 | CC2 | 30%

## Sheet3
line 1 | 500 | 2023-01-01
line 2 | 600 | 2023-01-01
line 3 | 400 | 2023-01-01
Rule 1
Line 1 | Amount = amount *2
Line 4 | Amount = Amount *5
View
2023-01-01 | line 1 | 1000
2023-01-01 | Line 2 | 600
2023-01-01 | Line 3 | 400